## Project Master
Task ID | Workstream | Activity | Description | LOB Owner | Start Date | Deadline | Status
1 | Infrastructure | NAS & Folder Setup | Confirm LOB-specific NAS paths & restricted permissions. | IT / LOB Lead | 2025-01-20 | 2025-02-05 | Not Started
2 | Development | Workflow Splitting | Dividing Master Alteryx Workflows into 4 LOB streams. | Automation | 2025-01-25 | 2025-02-12 | In Progress
3 | Access | License & Server | Provision Alteryx Designer & Gallery Designer roles. | LOB Lead | 2025-02-01 | 2025-02-10 | Not Started
4 | KT | Shadowing Sessions | Training LOBs on specific logic and error handling. | Automation | 2025-02-10 | 2025-02-20 | Not Started
5 | Testing | UAT & Parallel Run | Running split workflows vs. Master for Feb Month-End. | All LOBs | 2025-02-15 | 2025-02-26 | Not Started
6 | Handover | Final Sign-Off | Transfer of all SOPs and decommissioning old paths. | Enterprise | 2025-02-27 | 2025-02-28 | Not Started

## Knowledge Transfer
LOB Name | Trainee Name | Training Module | Session Type (Shadow/Reverse) | Date Completed | Assessment Result | Trainer Initial
LOB 1 | Jane Doe | Workflow Logic | Shadowing (Observe) | 2025-02-15 | Pass
LOB 1 | Jane Doe | Error Handling | Reverse Shadow (Lead) | 2025-02-22 | Pass
LOB 2 | John Smith | Monthly Recon | Reverse Shadow (Lead) | 2025-02-23 | Pass
LOB 3 | ... | ... | ... | ... | ... | ...

## Split NAS Drive
Alteryx Workflow Name | Original File Path (NAS) | New LOB Owner | New NAS Destination | Split Date | Reconciled? (Y/N) | Business Sign-off
Data Quality_Master_V1 | \\Corp\Shared\... | LOB 1 - Sales | \\LOB1\Finance\... | 2025-02-10
Data Quality_Master_V1 | \\Corp\Shared\... | LOB 2 - Ops | \\LOB2\Finance\... | 2025-02-11
Data Quality_Master_V1 | \\Corp\Shared\... | LOB 3 - HR | \\LOB3\Finance\... | 2025-02-11
Data Quality_Master_V1 | \\Corp\Shared\... | LOB 4 - Tech | \\LOB4\Finance\... | 2025-02-12